## Slide 1
Donkey Backlog — Status Review
Results Management · Smart Reports · Containerization · Migration Workflows
NPOCO project · PI32026 · 38 theme items · 68.5 SP
Generated by Ona

## Slide 2
Executive Overview
Where each theme stands across the Donkey backlog
Theme
Items
SP
% done (SP)
Unest.
Urgent/High
Results Management
9
5.0
60%
6
2
Smart Reports
6
8.0
75%
3
1
Containerization
9
24.5
43%
1
4
Migration Workflows
14
31.0
3%
7
6
TOTAL
38
68.5
30% done overall
17
13
Donkey POC — Backlog status by theme · NPOCO · PI32026
2

## Slide 3
Results Management
Progress (by SP)
60% complete
Items
9
Story points
5.0
Unestimated
6
Urgent / High
2
DONE
• NPOCO-26755 IRIS→RabbitMQ bridge
• NPOCO-27464 QC ACK to host
IN PROGRESS
• NPOCO-23174 Swipe blocks copy (Urgent)
TO DO / PARKED
• NPOCO-27648 QC autoreject
• NPOCO-27649 QC view improv.
• NPOCO-27647 QC improvements
• NPOCO-27839 RM integration
• NPOCO-27906 RM integration
• NPOCO-27031 RM spike (High)
⚠ Delivered work is event plumbing. All future QC/RM functionality is unestimated and parked in PI42026.
Donkey POC — Backlog status by theme · NPOCO · PI32026
3

## Slide 4
Smart Reports
Progress (by SP)
75% complete
Items
6
Story points
8.0
Unestimated
3
Urgent / High
1
DONE
• NPOCO-27600 iText spike
• NPOCO-27731 Replace PDF libs
IN PROGRESS
—
TO DO / PARKED
• NPOCO-27646 Smart reports MVP
• NPOCO-27657 Rebuild w/ nQC prompts
• NPOCO-27832 Config in POCM
• NPOCO-27297 AI patient-data spike (High)
⚠ 75% is misleading: only PDF-library groundwork is done. The actual Smart Reports product (MVP, nQC) is all unestimated and parked.
Donkey POC — Backlog status by theme · NPOCO · PI32026
4

## Slide 5
Containerization
Progress (by SP)
43% complete
Items
9
Story points
24.5
Unestimated
1
Urgent / High
4
DONE
• NPOCO-27265 Adapter skeleton I
• NPOCO-27311 DDA in docker
• NPOCO-27312 IRIS foundation
• NPOCO-27495 Knowledge transfer
IN PROGRESS
• NPOCO-27266 Adapter skeleton II (Urgent)
TO DO / PARKED
• NPOCO-26532 Gateway part II (High)
• NPOCO-27033 Gateway part III (High)
• NPOCO-27034 Gateway part IV (High)
⚠ Most advanced in real delivery: Adapter, DDA and IRIS containerized. The Gateway containerization stream is still fully open.
Donkey POC — Backlog status by theme · NPOCO · PI32026
5

## Slide 6
Migration Workflows
Progress (by SP)
3% complete
Items
14
Story points
31.0
Unestimated
7
Urgent / High
6
DONE
• NPOCO-26894 IRIS 2024.1.6 upgrade
IN PROGRESS
• NPOCO-27469 Comments endpoint (Urgent)
TO DO / PARKED
• NPOCO-27267 Org/Pract. migr. I (Urgent)
• NPOCO-27268 migr. II (Urgent)
• NPOCO-27269 migr. III (Urgent)
• NPOCO-27270 migr. IV (Urgent)
• NPOCO-26419 Win 2025 compat (8 SP)
• NPOCO-27638..42 Workflow parts I–V (parked)
• NPOCO-27739 One-time comments migr.
⚠ Highest risk: 31 SP, only 3% done, 6 Urgent items open, 7 unestimated, and the whole 'parts I–V' series parked in PI42026.
Donkey POC — Backlog status by theme · NPOCO · PI32026
6

## Slide 7
Key Takeaways & Risks
🔴 Migration Workflows = top risk
31 SP, only 3% done, 6 Urgent items open, 7 unestimated. The 'parts I–V' series is parked in the next PI. This is the bottleneck.
🟢 Containerization = most delivered
Adapter, DDA and IRIS are containerized. Remaining work is the Gateway stream (parts II–IV, High).
⚠ % done is misleading for Reports & RM
What shipped is infrastructure (PDF libs, event bridge), not product. The real features are unestimated.
📊 Estimation gap is critical
17 of 38 items (45%) have no story points, concentrated in Migration and parked features. Next-PI planning is at risk until estimated.
🅿 Parking lot = spillover signal
PI42026 parking lot: 4 Migration parts, 3 Results Mgmt, 2 Smart Reports, 1 Containerization — none prioritized yet.
Donkey POC — Backlog status by theme · NPOCO · PI32026
7

## Slide 8
Open Urgent Items — Action List
13 Urgent/High still open across themes
Key
Theme
Summary
Status
NPOCO-23174
Results Mgmt
Swipe gesture blocks text copy
In Progress
NPOCO-27266
Containerization
Adapter skeleton part II
In Progress
NPOCO-27469
Migration
Comments endpoint
In Progress
NPOCO-27267
Migration
Org/Practitioner migration part I
To Do
NPOCO-27268
Migration
Org/Practitioner migration part II
To Do
NPOCO-27269
Migration
Org/Practitioner migration part III
To Do
NPOCO-27270
Migration
Org/Practitioner migration part IV
To Do
NPOCO-26419
Migration
Windows 2025 compatibility (8 SP, unassigned)
To Do
NPOCO-26532
Containerization
Gateway containerization part II
To Do
NPOCO-27033
Containerization
Gateway containerization part III
To Do
NPOCO-27034
Containerization
Gateway containerization part IV
To Do
NPOCO-27031
Results Mgmt
Results Management spike
To Do
NPOCO-27297
Smart Reports
AI expose patient data spike
To Do
Donkey POC — Backlog status by theme · NPOCO · PI32026
8